## 2019
IGAP Work-plan / ETEP Evaluation
Tribal Priorities (From ETEP)
Environmental Program Management
Protection of Subsistence Resources
Water Quality and Supply
Salmon Subsistence Security
Contaminated Sites
Waste Management
Land Erosion
Climate Change Adaptation
Community Outreach and Education
Previous year's Work-plan Components | Tribal Priority addressed in previous year's work-plan | What Happened | When | Lessons Learned | New Ideas | Relate to ETEP Tribal Priorities? | Add to ETEP? | Add to new IGAP work-plan?
Travel and training - Staff will research available grants and management trainings. Staff will attend grants management trainings. Staff and Tribal Administrator will attend Quickbooks training | Environmental Planning & Ordinances | Staff attended a grant writing training and a Quickbooks training. IGAP funded the Tribal Administrators attendance at a Quickbooks training.The Tribal Administrator resigned, and a new Administrator was hired. | 1st quarter & 3rd quarter | Although the grant writing training was helpful, a grants management training is needed. | Research and attend a grant management training. Bring new Tribal Administrator to trainings for a better understanding of grants management. | Yes | In ETEP | Research and attend a advanced grant's management training.
Assess air pollution sources and concern Attend air quality training, read and collect information on the common sources of air pollution, complete a Phase 1 Air assessment, Schedule community meetings to provide education and outreach. | Community Outreach and Education | Staff attended an air quality basics training with ITEP. Completed ANTHC's Phase 1 air assessment and provided 2 community gatherings sharing information on the common sources of air pollution in a home. | 1st quarter, 2nd quarter, # 3rd quarter | Attending the training, completing an assessment and holding community gatherings were in the previous workplans but was not included as a tribal priority in our ETEP. | Meet with the Tribal Council and planning team to review and update the ETEP to include Air Quality as a tribal priority. Apply for ANTHC's Air project funding. | No | Yes | Air quality project.
Updated 01/2019